Project Planning Document (PPD)

Project Name: Vexa – AI-Powered Knowledge Hub

Version: 1.0
Date: August 21, 2025

Project Sponsor: [Name/Department]
Project Manager: [Name]
Document Status: Approved for Execution


1. Executive Summary
This document outlines the comprehensive plan for the development and launch of the Vexa Minimum Viable Product (MVP). Vexa is an AI-powered knowledge hub designed to consolidate note-taking, document management, and knowledge retrieval into a single, intelligent platform. This plan defines the project's scope, timeline, resources, budget, methodology, and risk mitigation strategies to ensure successful delivery within 10 weeks. The total estimated budget for the MVP phase is $299,000.


2. Project Scope

2.1. In Scope (MVP - Phase 1)

User Management: Secure user registration, login, and profile management using JWT-based authentication.

Core Knowledge Hub:

Rich Text Note-Taking: Create, Read, Update, Delete (CRUD) functionality with a basic rich text editor (bold, italics, lists).
Document Management: Secure upload, storage, and viewing of PDF and DOCX files (up to 25MB per file).
AI-Powered Summarization: Generate concise summaries of notes and uploaded documents via the Google Gemini API.
AI-Powered Quiz Generation: Automatically generate multiple-choice quizzes from user-provided notes.
Semantic Search: Meaning-based search across all user content (notes and documents) using vector embeddings

Basic Collaboration:

Ability to share individual notes with other users via a shareable link.
Real-time collaborative editing of shared notes using WebSockets.
Frontend Application: A responsive, single-page application (SPA) built with Next.js and Tailwind CSS, featuring a dashboard and light/dark mode.

Deployment & Infrastructure:

Frontend deployed on Vercel.
Backend microservices and PostgreSQL database deployed on AWS (leveraging the Free Tier initially).
Entire system containerized with Docker for consistency.

2.2. Out of Scope (Post-MVP)
Gamification (leaderboards, badges).
Voice/Chat AI assistant.
Full offline mode with sync.
Integrations with third-party platforms (Google Drive, Notion, OneDrive).
Blockchain-based verification.
Advanced team management and admin panels.
Native mobile applications (iOS/Android).

3. Project Methodology & Approach

Methodology: Agile-Scrum hybrid.

We will use a fixed-scope, time-boxed approach for the MVP, broken down into five 2-week sprints for development flexibility.

Tools:

Project Management: Jira (Scrum boards, backlog grooming, sprint planning).
Version Control: GitHub (feature branch workflow, pull requests).
CI/CD: GitHub Actions for automated testing and deployment.
Communication: Slack for daily updates, Microsoft Teams for scheduled meetings.
Documentation: Confluence for all project documentation.
Design: Figma for UI/UX mockups and prototypes.

Team Structure:

Project Manager (1)
UI/UX Designer (1)
Frontend Developers (1) - Next.js, Tailwind
Backend Developers (1) - Spring Boot, PostgreSQL, Kafka
AI/ML Engineer (1) - Gemini API integration, semantic search
QA Engineer (1)

4. Work Breakdown Structure (WBS) & Timeline
A detailed Gantt chart is provided in Appendix A. Below is the high-level milestone schedule.

| ID | Milestone | Description | Start Week | End Week | Owner |
| --- | --- | --- | --- | --- | --- |
| M1 | Project Initiation | Finalize team, setup tools, environments, and repos. | 1 | 1 | PM, Tech Lead |
| M2 | Authentication & DB Schema | JWT auth implemented. Finalized and implemented database schema. | 2 | 3 | Backend Team |
| M3 | Core Features Complete | Notes CRUD, Document Upload, and Summarization API integrated. | 3 | 5 | Full Team |
| M4 | Advanced AI & Collaboration | Quiz Generation, Semantic Search, and Real-time editing live. | 5 | 7 | AI Eng, Backend |
| M5 | Frontend Integration | All backend features integrated into the Next.js frontend. | 4 | 8 | Frontend Team |
| M6 | Testing & QA Sprint | Comprehensive testing, bug bashing, performance, and security audit. | 8 | 9 | QA Team |
| M7 | Deployment & Launch | Deployment to production (Vercel + AWS). Monitor initial launch. | 10 | 10 | DevOps, PM |
| M8 | Project Review | Retrospective, gather initial user feedback, plan Phase 2. | 10 | 10 | PM, Full Team |

5. Resource Allocation & Budget

| Resource Type | Count | Rate | Duration (Weeks) | Total Cost | Notes |
| --- | --- | --- | --- | --- | --- |
| Project Manager | 1 | $60/hr | 10 | $24,000 |  |
| UI/UX Designer | 1 | $50/hr | 10 | $20,000 |  |
| Frontend Developer | 2 | $55/hr | 10 | $44,000 |  |
| Backend Developer | 2 | $60/hr | 10 | $48,000 |  |
| AI/ML Engineer | 1 | $70/hr | 10 | $28,000 |  |
| QA Engineer | 1 | $50/hr | 10 | $20,000 |  |
| ** | Subtotal (Personnel) |  |  |  | $184,000 |  |
| ** |  |  |  |  |  |  |
| Cloud Infrastructure (AWS) |  |  |  | $5,000 | Dev, Test, Staging |  |
| Software Licenses (Jira, etc.) |  |  |  | $2,000 |  |  |
| Gemini API Credits |  |  |  | $8,000 | Estimated based on usage |  |
| ** | Subtotal (Tools & Services) |  |  |  | $15,000 |  |
| ** |  |  |  |  |  |  |
| Contingency (15%) |  |  |  |  | $29,850 |  |
| ** | Total Project Budget (MVP) |  |  |  | $228,850 |  |

- Risk Management Plan

A full Risk Regiester is maintained in Appendix B. Key risks include:

| Risk Description | Probability | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- |
| Scope Creep from stakeholder feature requests. | High | High | Strict change control process. All new features go into a "Phase 2" backlog. | PM |
| Gemini API costs exceed projections. | Medium | High | Implement response caching. Monitor usage dashboards daily. Set billing alerts. | AI Eng |
| Performance issues with real-time collaboration. | Medium | High | Start with a simple WebSocket implementation. Load test early and often. | Backend Lead |
| Security vulnerability (e.g., data leak). | Low | Critical | Schedule OWASP ZAP scans bi-weekly. Mandatory code reviews for security. | Tech Lead |
| Key team member becomes unavailable. | Low | High | Ensure knowledge sharing (pair programming, documentation). | PM |

- Communication Plan
Daily: 15-minute stand-up via Slack huddle.
Weekly: Sprint review/demo and planning meeting every other Monday.
Bi-Weekly: Status report email to stakeholders every second Friday.
Monthly: Steering committee meeting with executive sponsors.

8. Success Criteria & KPIs
On-Time Delivery: MVP launched within 10 weeks.
On-Budget Delivery: Project completed within ±5% of the allocated budget.
Quality: Zero Critical/High-priority bugs at launch. Application Performance Index (Apdex) score > 0.8.
User Adoption: 500 active users within the first month post-launch.
System Performance: 99.5% uptime in the first month. API response time < 200ms p95.

9. Appendices
Appendix A: Detailed Gantt Chart
Appendix B: Full Risk Register
Appendix C: Detailed Technical Architecture Diagram
Appendix D: UI/UX Mockups Link (Figma)

10. Signatures
This Project Plan has been reviewed and approved by:

Project Sponsor: _________________________
Print Name: _________________________
Date: _________________________

Project Manager: _________________________
Print Name: _________________________
Date: _________________________